## Response
Tri-Pack Films Limited
UATS-Employee Claims Portal
Dated: 13-May-25 |  |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-13
S.No. | List of Claims | Workflow | UATs Status by TPFL | Amount Calculation | Remarks- Control Doc Sheet | Remarks From IT
1 | Fuel - Mileage (within city) | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Pass | OK-Auto Calculated by system as per entitlement | Mileage amount calculation is correct for car and bike, whereas pls make the attachment field as mandatory to attach the snapshot of distance via google map for verification.
Pls evaluate that if Google Map Calculator is integrated with it.
2 | Local - Transport | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Pass | OK-Open Ended Field | Pls make attachment as mandatory for attaching the snapshot of payment on careen /in drive for verification purpose.
3 | Fuel - Receipts | Employee >> Accounts >> Completed | Pass | OK-Auto Calculated by system as per entitlement | UAT for this was done from Nimrah Asif (Grade M1) ID, the fuel limit is correct but plus mark attachment field as mandatory.
It will be used occasionally if fuel car is not working
4 | Local - Hotel Stay | Employee >> Line Manager >> BU Head >> Travel Manager >> Accounts >> Completed | Pass | OK-Open Ended Field | This is applicable for only cities where Company panel of hotels are not available. plus add this note.
Also plus mark attachment field as mandatory for payment receipts and travel order.
5 | Meal - Out of office (During Official Travel) | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Pass | OK-Open Ended Field | This is meal reimbursement during travel out of city.
Ok plus mark attachment field as mandatory for payment receipts and travel order and tickets
6 | Local - Toll tax / Parking charges / E-Tag | Employee>>Line Manager>>BU Head>>Accounts>>Completed | Pass | OK-Open Ended Field | Pls make attachment as mandatory for attaching the snapshot of toll tax receipts and travel order
7 | Misc. | Employee>>Line Manager>>BU Head>>Accounts>>Completed | Pass | OK-Open Ended Field | Pls make attachment as mandatory for attaching the snapshot of Payment receipts
8 | Medicines - Mother | Employee>>Accounts>>Completed | Pass | OK-Open Ended Field | Pls make attachment as mandatory for attaching the snapshot of Payment receipts and doctor's prescriptions.
We also have to add our Co. Doctor sb ID to it fordummy to test the workflow process.
Limits as per Packages to be followed
9 | Courier | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Pass | OK-Open Ended Field | Pls make attachment as mandatory for attaching the snapshot of Payment receipts
10 | Travel Order-Local | Employee>> Line Manager>> BU Head>> Travel Manager | Fail | Not Calculated | Pls remove the accomoadation option of Own-Arrangement, hotel by host country and hotel and food by host country, these option are not applicable for local travel. | In Travel order local - DA (Via Air) we have type of accomadation with the options of yes or no.
For local travel, co. do provide the hotel stay from the list of panel and co. guest house if available.
[5 empty] | Also, DA Amount is not calculated | DA Amount is not calucated in Travel Order. It calculates when the employees applys for the travel claim
11 | Tavel Order-Foreign |  | Fail | Not Calculated | No of Days are correct but DA mount is not calculated | DA Amount is not calucated in Travel Order. It calculates when the employees applys for the travel claim
12 | Local - DA | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Fail | Incorrect | Daily Allowance amount is incorrect. Per Day entitlement for E2 Grade is PKR 1600 but here it's 900/day. Pls correct it. Also make attachment as mandatory for attaching the travel order and air tickets. | This has been resolved, please verify and let us know if there any further issues
13 | Foreign - DA | Employee >> Line Manager >> BU Head >> MD >> Accounts >> Completed | Fail | - | The travel order dropdown is not working due to which unable to submit the claim | Travel order process has to completed end-to-end, after that it will be visible in the drop down. As shown in the attached screenshot.
14 | Meal - Entertainment | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Pass | OK-Open Ended Field | Ok claim exceeding 25k goes to Nasir Jamal CE for Approval.
Comment need to be added if amount is exceeding the limit the exception approval goes to CE.
15 | Mobile - Handset | Employee>>Accounts>>Completed | Fail | NO | If the entered amount (PKR 45,000) is less than or equal to the entitled amount (PKR 55,000 E2 Grade Entitlement), the system should allow submission of the entered amount. | This has been resolved, please verify and let us know if there any further issues
If the entered amount exceeds the entitled amount, the system should prevent submission and display PKR 55,000.
Pls note that gate check of mobile claim must be with EC Portal.
16 | Local - DA (via Air) | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Fail | Not Calculated | The travel order dropdown is not working due to which unable to submit the claim | Travel order process has to completed end-to-end, after that it will be visible in the drop down. As shown in the attached screenshot.
[5 empty] | Pls remove the accomoadation option of Own-Arrangement, hotel by host country and hotel and food by host country, these option are not applicable for local travel. | This is in-process and will be done in next few days, and yes and no values will be displayed under the accommodation drop down.
For local travel, co. do provide the hotel stay from the list of panel and co. guest house if available.
Also, DA Amount is not calculated
17 | Medical - OPD | Employee >> Accounts >> Completed | Fail | Incorrect | There are no policy gate checks are applied | The limits are visible now, please verify and let us know if there are any concerns on this. (For now, the limits are dummy, at the time of cutover, original values will be inserted into the system)
No annual medical limit is visible/or maintained in system
18 | Mobile - Card / PTCL | Employee>>Line Manager>>BU Head>>Accounts>>Completed | Not Required | Not Required | -
19 | Fuel - Mileage (out of city) | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Not Required | Not Required | Fuel Milleage rate for within and out of city is same for both car and bike.
20 | Local - Toll tax / Parking charges / E-Tag (out of city) | Employee >> Accounts >> Completed | Not Required | Not Required | This covered in S. No. 06 of Local-Toll Tax
21 | Meal - Out of Lahore Posting | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Not Required | Not Required | Not Required
22 | Local - Excise Token Tax | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Not Required | Not Required | Not Required
23 | Employee Amenities-Guest house/Rest house | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Not Required | Not Required | Not Required
24 | Employee Amenities-Sales office | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Not Required | Not Required | Not Required
25 | Vehicle Repair/Maintenance | Employee >> Line Manager >> BU Head >> Accounts >> Completed | Not Required | Not Required | Not Required